## GeneralPlan
	Motivation	To meet the future need of the Turkish Aerospace in developing hypersonic aerospace vehicles

	Objective	Developing a transient, compressible, two-temperature, 3D, Implicit semi-coupled, thermochemical non-equilibrium hypersonic CFD solver. This solver shall be able applicable in the continuum-transition regime (1.0 > Knudsen number > 0.2).

	Scope	OpenFOAM will be the development platform, tamsAero will be used for solving the conservative variables (rho rhoU rhoE) as a coupled system, whereas the turbulence model, the second temperature equation and the specie transport equations will be solved sequentially. Furthermore, the chemical reactions will be handled akin to the reactingFoam capabilities. The ionization processes are not considered since the electronic energy mode is omitted.

		February-March		April-June		June	July	August	September	October	November	December-January
Task No	Task Description	Semester 1				Summer Break-I			Semester 2				Semester 3				Summer Break			Semester 4
1	Understanding the governing equations, and the required computational sub-modules
2	Listing the required modifications/new implementations for each part of the code
3	Deciding the solver execution sequence and the code integration methods with sub-modules
4	Deciding Test Cases & Running Test Cases with Literature Solvers
5	New thermodynamic library (Implementation & unit testing)
6	Chemical and energy source terms of two-temperature model (Implementation & unit testing)
7	Vibration energy equations [rhoE_v_m for each m], convection, and diffusion terms (Implementation & unit testing)
8	Chemical reactions (Implementation & unit testing)
9	Specie transport equations [rho_s, for each s] (Implementation & unit testing)
10	Conserved variables (rho rhoU rhoE) part: For instance, modifying the viscous flux in the energy equation, Dalton’s law etc.
11	Integrating all the sub-parts of the code
12	Validating the solver, comparisons with experimental and numerical (SU2_NEMO, Eilmer etc.) results
13	Publication (paper & thesis)

Legend			Important Note
	Not Started		These timelines are subjected to change alongside development and research process. Future semesters are just predictions, not unchangeable deadlines.
	Currently
	Completed
	Incompleted within time limits

## Semester1
		Motivation	Understanding the governing equations, and the required computational sub-modules alongside listing the required modifications/new implementations for each part of the code

		Objective	Developing pretty-well understanding of governing equations, capability to read OpenFOAM solver source code, consuming all of the noteworthy literature about external flow solvers with chemical reactions in OpenFOAM, and creating modifications/implementations list of the TAMS-AERO code

		Start Date	17.02.2025					End Date			23.06.2025

			February		March				April					May				June
Sub Task No	Main Task Description	Sub Task Description	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13	Week 14	Week 15	Week 16	Week 17	Week 18
1	Understanding the governing equations, and the required computational sub-modules	Overall literature study for relevant open source for hy2Foam
2		Selection and compilation of the relevant open source hy2Foam
3		Overall literature study for relevant open source Eilmer
4		Selection and compilation of the relevant open source Eilmer
5		Overall literature study for relevant open source SU2-NEMO
6		Selection and compilation of the relevant open source SU2-NEMO
7		Test Case Simulations for hy2Foam, Eilmer, SU2-NEMO
8		Examination of implementation of chemical reactions within the relevant solvers
9	Listing the required modifications/new implementations for each part of the code	Literature study of hyperReactingFoam and reactingRhoCentralFoam solver
10		Compilation and examination of the rhoCentralFoam
11		Compilation and examination of the reactingRhoCentralFoam
12		Extracting the implementation/modification list out of hyperReactingFoam
13	Deciding the solver execution sequence and the code integration methods with sub-modules	Constructing an initial algorithm extracted from examined solvers
14		Deciding thermodynamical and chemical libraries that are going to be employed within code
15		Deciding module implementation schedule for development

Legend
	Not Started
	Currently
	Completed
	Incompleted within time limits

## TestCases
		Motivation	Understanding the governing equations, and the required computational sub-modules alongside listing the required modifications/new implementations for each part of the code

		Objective	Developing pretty-well understanding of governing equations, capability to read OpenFOAM solver source code, consuming all of the noteworthy literature about external flow solvers with chemical reactions in OpenFOAM, and creating modifications/implementations list of the TAMS-AERO code

		Start Date	01.06.2025					End Date			31.08.2025

			June 8	June 15	June 22	June 29	July 6	July 13	July 20	July 27	August 3	August 10	August 17	August 24	August 31
Sub Task No	Main Task Description	Sub Task Description	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13
1	Reacting Air with Thermal Equilibrium Inside Thermal Heat Bath	Preparing Mesh
2		hy2Foam Run
3		SU2-NEMO Run
4		Eilmer5 Run
5		Post-processing
1	Remaining Thermal Heat Bath Cases	Preparing Mesh
2		hy2Foam Run
3		SU2-NEMO Run
4		Eilmer5 Run
5		Post-processing
1	Blunted Cone	Preparing Mesh
2		hy2Foam Run
3		SU2-NEMO Run
4		Eilmer5 Run
5		Post-processing
1	Double Wedge	Preparing Mesh
2		hy2Foam Run
3		SU2-NEMO Run
4		Eilmer5 Run
5		Post-processing

Legend
	Not Started
	Currently
	Completed
	Incompleted within time limits