## GeneralPlan
	Motivation	Why this project?

	Objective	Practical main goal that is in line with motivation

	Scope	Restrictions which make objective possible within given timeline

	Start Date	xx.xx.xxxx					End Date			xx.xx.xxxx

Task No	Task Description	Month 1				Month 2				Month 3				Month 4				Month 5				Month 6
1	Understanding the governing equations, and the required computational sub-modules
2	Listing the required modifications/new implementations for each part of the code
3	Deciding the solver execution sequence and the code integration methods with sub-modules
4	Chemical reactions (Implementing them separately (Isolating this part from reactingFoam) & unit testing)
5	Specie transport equations [rho_s, for each s] (Implementing them separately (Isolating this part from reactingFoam) & unit testing)
6	New thermodynamic library (Implementation & unit testing)
7	Vibration energy equations [rhoE_v_m for each m], convection, diffusion and source terms (Implementation & unit testing)
8	Conserved variables (rho rhoU rhoE) part: For instance, modifying the viscous flux in the energy equation, Dalton’s law etc.
9	Integrating all the sub-parts of the code
10	Validating the solver, comparisons with experimental and numerical (SU2_NEMO, Eilmer etc.) results
11	Publication (paper & thesis)

Legend
	Not Started
	Currently
	Completed
	Incompleted within time limits

## Semester1
		Motivation	Task which is described generally in the main timeline

		Objective	Practical goals that are achievable within weeks

		Start Date	xx.xx.xxxx					End Date			xx.xx.xxxx

Sub Task No	Main Task Description	Sub Task Description	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13	Week 14	Week 15	Week 16	Week 17	Week 18
1	Understanding the governing equations, and the required computational sub-modules	Overall literature study for relevant open source for hy2Foam
2		Selection and compilation of the relevant open source hy2Foam
3		Overall literature study for relevant open source Eilmer
4		Selection and compilation of the relevant open source Eilmer
5		Overall literature study for relevant open source SU2-NEMO
6		Selection and compilation of the relevant open source SU2-NEMO
7		Test Case Simulations for hy2Foam, Eilmer, SU2-NEMO
8		Examination of implementation of chemical reactions within the relevant solvers
9	Listing the required modifications/new implementations for each part of the code	Literature study of hyperReactingFoam and possible relevant open source CFD solvers
10		Compilation and examination of the selected solver
11		Extracting the implementation/modification list out of selected solver

Legend
	Not Started
	Currently
	Completed
	Incompleted within time limits